## Feuil1
SEPM standard and/or EP | Topic | Detailed Steps |  | Calendar | [11 empty] | Expected output/deliverable | Person(s) in charge | Department | Priority | Deadline | LOE/ Budget
Year 1
|  |  |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
1B | Improvement and sytematization of customer data analysis | 1.1 | Check the information available in the MIS | [13 empty] | SEP Committee | IT | bar: Year 1 M2
|  | 1.2 | Discussion of potential indicators, interesting results to analyze, use of information | [13 empty] | SEP Committee | IT | bar: Year 1 M3
|  | 1.3 | Generating the chosen indicators | [13 empty] | SEP Committee | IT | bar: Year 1 M4
|  | 1.4 | Discussing which indicators (aggregation/disaggregation) would be useful | [12 empty] | List of indicators | SEP Committee | IT | bar: Year 1 M5
|  | 1.5 | Adaptation & adjustments | [13 empty] | SEP Committee | IT | bar: Year 1 M6
|  | 1.6 | Pre-report based on customer information | [13 empty] | SEP Committee | IT | bar: Year 1 M7 to Year 1 M8
|  | 1.7 | Annual report including customer data | [12 empty] | Annual social report | SEP Committee | Management/Operations | bar: Year 1 M9 to Year 1 M10
|  | 1.8 | Finalization of a social dashboard for the board and management | [12 empty] | Social dashboard | SEP Committee | Management/Operations | bar: Year 1 M11 to Year 1 M12
4E | Clients' complaints mechanisms | 2.1 | Analysis of current practices | [13 empty] | SEP Committee | Operations | (1) Quick-win | bar: Year 1 M2
|  | 2.2 | Define a process for complaints procedures | [13 empty] | SEP Committee | Operations | (1) Quick-win | bar: Year 1 M2
|  | 2.3-2.5 | Manual for complaints management | [12 empty] | Procedures | SEP Committee | Operations | (1) Quick-win | bar: Year 1 M3 to Year 1 M7
|  | 2.6 | Training of the loan officers | [12 empty] | Staff aware | HR Trainers | HR | (1) Quick-win | bar: Year 1 M7 to Year 1 M10
|  | 2.7 | Information to clients on the complaint mechanism | [12 empty] | Clients aware | Loan officers | Front office / Operations | (2) Medium-term priority | bar: Year 1 M7 to Year 1 M8
|  | 2.8 | First report on the complaints and use of the results from clients to improve products and services | [12 empty] | Improve products | Management | Management/Marketing | (2) Medium-term priority | bar: Year 1 M12

## Feuil2 (hidden)
(1) Quick-win
(2) Medium-term priority
(3) Long-term priority