## Template
ACTION PLAN - AGRI ASSESSMENT | [17 empty] | Version: August 2026 Draft version, under development
Tool | Dimension / Standard | Topic | Detailed Steps |  | Calendar | [11 empty] | Expected output/deliverable | Person(s) in charge | Department | Priority | Deadline | Level Of Effort (LOE) | Budget | Cost Implication
[5 empty] | Year 1 | [17 empty] | Budget
[5 empty] | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
RAI | Dimension 2 Inclusive & Transparent Governance Structure 2.C | Stakeholder grievance mechanism strengthening | 2.1 | Assess current grievance management practices against RAI Standard 2.C requirements | [12 empty] | Gap Assessment Report | Compliance Officer | Compliance / Operations | Quick-win | M1 | 3 person-days |  | Moderate Cost | bar: Year 1 M1
|  |  | 2.2 | Define grievance handling procedures (intake, acknowledgement, investigation, resolution, appeal) | [12 empty] | Grievance Procedure | Compliance Officer | Compliance | Quick-win | M2 | 5 person-days |  | Moderate Cost | bar: Year 1 M2
|  |  | 2.3 | Establish a centralized grievance recording system (register / digital database) | [12 empty] | Grievance Register | Compliance Officer / IT Manager | Compliance / IT | Quick-win | M3 |  | $1,500 | No or Low cost | bar: Year 1 M3
|  |  | 2.4 | Define response and escalation timelines and procedures | [12 empty] | Escalation Protocol | Compliance Officer | Compliance | Medium-term priority | M4 | 3 person-days |  | Moderate Cost | bar: Year 1 M4
|  |  | 2.5 | Train staff and field officers responsible for complaint intake and handling | [12 empty] | Training Report | HR Manager / Compliance Officer | HR / Compliance | Medium-term priority | M5 |  | $2,000 | Moderate Cost | bar: Year 1 M5
|  |  | 2.6 | Inform farmers, suppliers, workers and communities about available grievance channels (local languages) | [12 empty] | Awareness Materials | Field Operations Manager | Operations / Community Engagement | Medium-term priority | M6 |  | $1,000 | No or Low cost | bar: Year 1 M6
|  |  | 2.7 | Produce periodic grievance analysis reports and feed lessons learned into management decisions | [12 empty] | Periodic Grievance Reports | Compliance Officer / Director | Compliance / Management | Medium-term priority | M9 | Ongoing |  | No or Low cost | bar: Year 1 M9
Agri CP | CP2 Prevention of Over-Indebtedness 2.A | Strengthening repayment-capacity-based loan decisions | 2.1 | Assess current loan appraisal and affordability assessment practices against Agri-CP Standard 2.A | [12 empty] | Gap Assessment Report | Credit Manager | Credit | Quick-win | M1 | 3 person-days |  | Moderate Cost | bar: Year 1 M1
|  |  | 2.2 | Define a standardized affordability / cash-flow assessment methodology by crop type and farm profile | [12 empty] | Affordability Assessment Methodology | Credit Manager / Risk Manager | Credit / Risk Management | Quick-win | M2 | 5 person-days |  | High Cost | bar: Year 1 M2
|  |  | 2.3 | Integrate market price, seasonality and climate risk data into the repayment-capacity model | [12 empty] | Updated Credit Scoring Model | Risk Manager | Risk Management | Medium-term priority | M4 |  | $3,000 | Moderate Cost | bar: Year 1 M4
|  |  | 2.4 | Train credit and loan officers on the revised affordability assessment methodology | [12 empty] | Training Report | HR Manager / Credit Manager | HR / Credit | Medium-term priority | M5 |  | $2,000 | Moderate Cost | bar: Year 1 M5
|  |  | 2.5 | Pilot the revised methodology in selected branches/regions and evaluate results | [12 empty] | Pilot Evaluation Report | Credit Manager | Credit | Medium-term priority | M7 | 4 person-days |  | Moderate Cost | bar: Year 1 M7
|  |  | 2.6 | Roll out the revised loan appraisal procedure organization-wide and monitor over-indebtedness indicators (PAR, multiple borrowing) | [12 empty] | Revised Loan Appraisal Procedure / Portfolio Monitoring Dashboard | Credit Manager / Risk Manager | Credit / Risk Management | Long-term priority | M10 | Ongoing |  | Moderate Cost | bar: Year 1 M10

## Feuil1 (hidden)
Quick-win
Medium-term priority
Long-term priority
No or Low cost
Moderate Cost
High Cost